## Sheet1
S.No | Task | Description | Time
1 | Login screen update with New UI | Login screen update with New UI | 3
2 | Create Dashboard screen for Immigrant | Home screen UI design and functionality | 3
3 | Create Dashboard screen for solicitor | calling Home screen UI design and functionality | 2
4 | Create Dashboard screen for barrister | Home screen UI design and functionality | 2
5 | Floating Icon functionality for creating notifications in the dashboard. | Floating Icon functionality for creating notifications in the dashboard.
6 | The user should able to view or delete notification. | The user should able to view or delete notification.
7 | Status of the user case update from Solicitor or Barrister for Approve or reject. | Status of the user update from Solicitor or Barrister for Approve or reject of case UI and functionality with API integration. If immigrant tries to open the app it should navigate login page (Not Dashboard screen )and show the alert message Dear User your case is closed please register again" the same for if immigrant tries to log in "
8 | Save documents in a secure way in the mobile app. | Save documents in a secure way in the mobile app.We should not share the downloaded documents to other apps.
9 | Status of the user update API change | Status of the user update API side change
10 | Status of the user update Database change | Status of the user update Database change
11 | video call filename, size, duration, timestamp and single, double and triple profile icons. | video call filename, size, duration, timestamp and single, double and triple profile icons.
12 | Manual Testing dashboard in the Immigrant screen | Test case for dashboard in the immigrant screen.
13 | Manual Testing dashboard in the solicitor screen | Test case for dashboard in the solicitor screen.
14 | Manual Testing dashboard in the barrister screen | Test case for dashboard in the barrister screen.

## Sheet2
S.No | Function / Task | UI | Service | Change | Change Effort | Est DoC | Resource | Time | Comment
1 | Login Immigrant | N | Y
2 | Registration for immigrant | N | Y
3 | upload file Immigrant
4 | Get notification immigrant
5 | Dashboard in Immigrant
6 | download file in immigrant
Video download in Immigrant
7 | Share file in Immigrant
8 | React according to case status in login screen
9 | dropdown to access immigrant in the dashboard for solicitor and barrister.
10 | Login solicitor
11 | Dashboard in solicitor(download,share,video call list,notification,case update and send notification)
12 | Immigrant list in solicitor
13 | Video call log functionality
14 | Delete/inactivate Barrister
15 | Delete/inactivate Immigrant
16 | Get notification Solicitor
17 | Login barrister
18 | Registration for barrister
19 | Dashboard in barrister
20 | Immigrant list in barrister
21 | accept and reject in the cases(barrister)
22 | DB changes
23 | API services changes
24 | UI and API functionality for case status
25 | UI and API functionality for case status for video call logs